## Sheet1
| Anglian Water Independent Challenge Group - Challenge log for PR24 BY SUBJECT |  |  | 2023-09-29
Item | Subject | Date raised | Category (information request, action, challenge) | Comment/feedback/challenge | Response/action | Date closed | Status (open/closed)
Affordability/vulnerability
160 | Affordability/vulnerability | 15 September 2023 ICG meeting | Challenge | In customer research on support for vulnerable customers, were customers given any other reason for increase in cross subsidies than bill increase? | Research was done in context of 2022/23 bills rather than increase over next AMP. Increase in cross subsidy is a nominal amount, not automatically indexed. | 15 September 2023 ICG meeting | Closed
138 | Affordability/vulnerability | 30 June ICG meeting | Challenge | What is the overall impact the affordability/vulnerability programme will have on the Business Plan (and bills)? Have customer views been tested on this specifically? Will any increase in support include more money from the company itself, or will it just be paid for through an increased cross-subsidy from customers? | Addressed at ICG meeting 30 June and also covered at 15 September 2023 ICG meeting. | 15 September 2023 ICG meeting | Closed
139 | Affordability/vulnerability | 30 June ICG meeting | Challenge | What proportion of customers were in the 5% of income water poverty bracket and what proportion were getting support? ICG wanted to see a glide path towards support for 8% of customers living in water poverty. How effective were the programmes at lifting customers out of water poverty? | Addressed at 15 September 2023 ICG meeting | 15 September 2023 ICG meeting | Closed
140 | Affordability/vulnerability | 30 June 2023 ICG meeting | Challenge | ICG members commended AW’s offering and asked how they planned to increase awareness among the most difficult-to-reach customers | AW colleagues mentioned using partnerships and independent third parties to reach out to a wider customer base, particularly through social housing partnerships. There was an opportunity presented by smart meter rollouts to engage with customers and maximise PCC benefits | 30 June 2023 ICG meeting | Closed
141 | Affordability/vulnerability | 30 June 2023 ICG meeting | Challenge/information | Members asked about innovative tariffs for non-household customers. | This work is ongoing - including work with Blue Marble | 30 June 2023 ICG meeting | Closed
65 | Affordability/vulnerability | 6 Oct 2022 ICG meeting | Challenge/information | How is AW supporting household and non-household customers? | AW highlighted the opportunity presented by smart meter rollouts to engage with customers and maximise PCC benefits. | 6 Oct ICG 2022 meeting | Closed
66 | Affordability/vulnerability | 6 Oct 2022 ICG meeting | Challenge/information | How have customer views on affordability changed since PR19? | Addressed through agenda and pre-reading for 6 October 2022 meeting. | 6 Oct ICG 2022 meeting | Closed
42 | Customer engagement/vulnerable customers | 18 July 2022 ICG meeting | Challenge/information | Has AW done enough to understand the views of specific customer segments - in particular to understand the priorities and preferences of hard-to-reach customers. | To be covered at 30 June ICG. As part of the overall assurance, we have covered all relevant demographics and customer types. | 30 June 2023 ICG meeting | Closed
4 | Vulnerable customers | 19 March 2021 CEF Meeting | Information | What kind of engagement took place in relation to the Covid pandemic, particularly in relation to vulnerable customers. | Response: AW reached out to hundreds of thousands of customers to understand their needs. The industry has come together on this, particularly around shielding customers. But there’s still more to be done. Lots of research was done through the Customer Panel - and a positive difference fund was launched. | CEF Meeting 19 March 2021 | Closed
3 | Vulnerable customers | 19 March 2021 CEF Meeting | Challenge | Customer engagement needs to be ongoing and a business as usual activity. Triangulation is really important and there is work to be done in terms of vulnerable and hard to reach customers. Some of these customers felt they were a bolt on to the rest of the research. | Response: AW agreed that customer engagement is not just for price reviews. AW carries out CE because it wants to understand what customers want and need. AW would do that regardless of the Ofwat process. Response: In terms of vulnerable customers, AW tried to co-create with customers and tried to engage with them in the way they wanted in PR19. Regional differences and customer experiences are different across the AW region and across the country and this needs to be taken into account. | CEF Meeting 19 March 2021 | Closed
Performance commitments
157 | ODIs and PCs | 15 September 2023 ICG meeting | Challenge | How did AW plan to respond to direction from Ofwat on common PCs and ODIs? Why was AW rejecting Ofwat methodology on some common PCS and not others? | AW was adopting Ofwat's central incentive rates for all but four PCs where they believed they had more compelling and stronger customer insight. | ICG meeting 15 September 2023 | Closed
151 | ODIs | 25 July 2023 ICG Meeting | Challenge | ICG raised concerns about the challenge of cutting water consumption by 10% in the face of projected housing growth. Different plans submitted by AW had subtly different focuses and needed to be more joined up. | It was always at the top of AW’s agenda to make sure that customers had enough water; this is enshrined in the WRMP. It would be helpful to come back to the ICG in September to make sure that all the themes in the different plans had been drawn together. | This was not discussed in detail at the 15 Sept meeting due to lack of time | Open
152 | ODIs | 25 July 2023 ICG Meeting | Challenge | ICG questioned how challenging some targets were considering some targets had been missed in previous years (e.g. on water supply interruptions). Were targets ambitious enough? It would also be helpful to see three-year rolling performance rather than just year on year company performance. | Ambitions for improvement were stretching, even if AW was behind on performance targets in some areas. The increased frequency of extreme weather events (particularly in 2022) was challenging. It might be helpful to look at a three-year average for some performances measures to smooth out the volatility created by extreme events in some years. | Information was provided in August 2023 | Closed
153 | ODIs | 25 July 2023 ICG Meeting | Challenge | Overall members were heartened by the focus on re-prioritising according to customers’ views and felt that the four focus areas were obvious candidates but they would like to see more focus on biodiversity. | It would be helpful to bring back discussions on biodiversity to a future ICG meeting (including one of his colleagues, who chaired the Ofwat working group that developed the biodiversity metric). | To be discussed at a future ICG meeting Being discussed at 8 December meeting | Open
154 | ODIs | 25 July 2023 ICG Meeting | Challenge | There was a question about effectively reducing incentive rates around the total pollution and serious pollution incidents, and how this fits in with the PIRP. | Answered at 25 July 2023 ICG meeting (see minutes) | ICG meeting 25 July 2023 | Closed
123 | Bespoke performance commitments | 17 March 2023 ICG meeting | Challenge/question | Had support from customers and stakeholders been gathered for the proposed bespoke PCs? There was a lot of overlap with common PCs. | More information would be shared at a future meeting. | ICG meeting 16 June 2023 | Closed
124 | Bespoke performance commitments | 17 March 2023 ICG meeting | Challenge | A bespoke PC needed to show “significant additional benefits for customers that are unlikely to be realised without it”. ICG felt they hadn’t seen that yet in AW’s bespoke PCs - or specificity to region. | We are assessing Ofwat's feedback on bespoke performance commitments. We will provide more details to the ICG on those we decide to proceed with in the business plan. | ICG meeting 16 June 2023 | Closed
125 | Bespoke performance commitments | 17 March 2023 ICG meeting | Challenge | Improving river and ecology was something AW should be doing through WINEP so the Environment Agency wouldn’t be able to support that as a bespoke PC. | As above | ICG meeting 16 June 2023 | Closed
126 | Bespoke performance commitments | 17 March 2023 ICG meeting | Challenge | It was a shame that the proposed bespoke PC on nutrient neutrality didn’t include water demand neutrality. It could be something that’s over and above that AW could work with local authorities on. | We did consider this in formulating the performance commitment but concluded Ofwat would consider it an overlap with the PCC performance commitment. | ICG meeting 16 June 2023 | Closed
27 | Performance commitments/biodiversity | 18 July 2022 ICG meeting | Challenge/information | Did AW have concerns around the changes in ODIs, particularly around biodiversity? | We are supportive of the principle of the biodiversity performance commitment. We are working through the definition but are encouraged that it enables flexibility in including sites or areas that offer the best potential to improve biodiversity. If the ICG would still like to discuss further, we'd be happy to present how the PC is being defined. | ICG Meeting 18 July 2022 | Closed
34 | Performance commitments | 18 July 2022 ICG meeting | Challenge/information | Where does bespoke research fit in? Was AW currently thinking of any bespoke performance commitments. | We've undertaken a significant amount of research on the bespoke performance commitments through a number of channels. This includes reviewing the customer synthesis report for existing views on priorities, online community engagement on decription clarity and priority, the research with Trinity McQueen on priorities and the research with ICS on incentives for bespoke performance commitments. The ICG sub-panel saw the research materials for Trinity McQueen and ICS and we action the feedback before they went live. If any further changes are made to bespoke performance commitments, we will consider the need for further customer engagement. Reference at 16th June meeting to 1) first stage of online community research 2) the second stage at online community 3) Trinity McQueen and 4) ICS. | ICG meeting 18 July 2022 | Closed
Company performance
156 | Company performance | 15 September 2023 ICG meeting | Challenge | What is the distribution between enhancement and base Totex? | Increase in base Totex is due to increase in energy costs, which is a sectoral issue. | ICG meeting 15 September 2023 | Closed
154 | Company performance/risk profile | 30 July 2023 ICG meeting | Challenge | The changing climate may change the risk profile of the company. ICG asked how AW was responding to that and making sure they were more resilient? | In the short term, AW needs to benchmark themselves against other companies and look at where improvement was needed. In the longer term, their response to the resilience challenge was the proposal for two new reservoirs. In the APR, there’s a section about the risk assessment that the Board undertakes. | ICG meeting 30 July 2023 | Closed
131 | Company performance | 17 May 2023 ICG only | Challenge/question | How do AW make performance information available to their customers and how their transparency compares with other companies; whether there are areas they could do more on. (It would be useful to have an interactive hub and comparators across the water industry). | AW colleagues have agreed to share quarterly updates with the ICG on company performance but have not yet confirmed arrangements for sharing the information publicly. Service Commitment Plan published 30 November and updated to be provided 31 Jan and 30 April on our website. Seperately taking forward a Purpose performance dashboard to be available in 2024. |  | Open
132 | Company performance | 17 May 2023 ICG only | Challenge/question | Another issue that keeps coming up in the media is Anglian's complex structure and its practices on external and internal dividend and debt payments. From a customer point of view is it in their interests, neutral or not in their interests in terms of the service they get and the bills they pay now and into the future. | From an AW perspective, we would highlight the significant investment in our region and long term security of our ownership model. The business changed its articles of association to legally link to our purpose (bringing Environmental and Social prosperity to the region we serve). This means, Directors of the company are legally obliged to consider our customers, our shareholders and our purpose in decisions. Returns to our shareholders is not the only factor that is front of mind. We need to be mindful that the returns on ownership are generally reducing and to maintain long term stable ownership models must include the ability for companies to give returns | Written response | Closed
107 | Policy | 20 Jan 2023 ICG meeting | Challenge | Members flagged the need to influence policy to help impact certain areas that would have an influence for customers (e.g. building regulations). | AW reached out to individual ICG members for a discussion offline re opportunities for AW to get more involved with planning and the implications of this on water resources (and behavioural change) | Follow up from 20 January 2023 ICG meeting | Closed
87 | Company performance/due diligence | 9 Dec 2022 ICG meeting | Challenge/information | What was AW response to media coverage suggesting that water companies had incurred debt to fund dividends. | Response from AW at ICG meeting: AW had only just started paying dividends again after six years. Payments are in line with what’s assumed as a fair return for an investor in this sector. Outlandish dividends happened historically and aren’t happening at all now. There needs to be a control around dividends that reflect performance of company. | ICG meeting 9 December 2022 | Closed
23 | Compliance | 10 May 2022 Email shared | Challenge/information | What are the implications/ramifications of the EA/Ofwat investigations into mis-reporting of wastewater compliance/CSO spills | Addressed during May 2022 ICG meeting | Email shared at ICG meeting 10 May 2022 | Closed
2 | Bill impact | 19 March 2021 CEF Meeting | Information | What impact would the CMA decision have on customer bills? | Response: the original AW Business Plan would have seen a slight decline in bills for customers. The Ofwat determination drove bills down much lower. CMA is somewhere between those positions. There will be no change to bills until Year 3 of this AMP. | CEF Meeting 19 March 2021 | Closed
5 | Company performance/PCscommitments | 19 March 2021 CEF Meeting | Action/information | It would be useful to see performance indicators in advance of the next CEF meeting to help with scrutiny. | ICG was given a full performance update slidepack by Brian Ebdon at the April 2023 ICG meeting and AW colleagues agreed to share a quarterly performance update. | ICG Meeting 21 April 2023 | Closed
Customer engagement
161 | Affordability & Acceptability Testing | 15 September 2023 ICG meeting | Challenge | What would AW use results from the shadow survey for? Would they form part of BP submission? | This was still a live discussion but figures from the mandated survey would most likely be used in the BP, with an explanation of the shadow survey in the narrative. Confirmed used mandated survey in data tables | ICG meeting 15 September 2023 | Open
149 | Customer engagement | 30 June 2023 ICG meeting | Challenge/question | Was there any mapping of customer engagement; could it be visually represented? | Clear quotas were set at the beginning of the engagement programme through customer segmentation. A visual representation had been considered in demonstrating how all areas across the region had been engaged, but not all research fits into these segments eg capturing our business as ususal insight, Ofwat’s centralised research and the online community where we cant specify who takes part. However, there are quotas for each area in the segmentation strategy that both AW and their external partners have abided by in research design. | 30 June 2023 ICG meeting | Closed
132 | Affordability & Acceptability Testing | 16 June 2023 ICG meeting | Challenge/question | Members questioned the use of nine buckets instead of the proposed six by Ofwat, and the potential for re-categorisation if Ofwat pushed back on this | The message from Ofwat to AW and other companies was to consult with their ICGs where any changes to the standard guidance may be considered. ICG members expressed support for sharing nine headings instead of six; it seemed like the right approach. It was important for the ICG to understand whether AW was meeting all statutory requirements. | ICG meeting 15 September 2023 | Closed
133 | Affordability & Acceptability Testing | 16 June 2023 ICG meeting | Challenge/question | Has AW discussed with Ofwat how they had presented their BP to customers in the A&A qualitative phase, since it wasn’t exactly what Ofwat had asked for? | AW called it the ‘alternative plan’ because their statutory plan wasn’t least cost, but the details shared with customers were consistent with the guidance. | ICG meeting 15 September 2023 | Closed
134 | Customer engagement | 16 June 2023 ICG meeting | Challenge/question | The ICG’s Task and Finish Group had seen a version of the slides presented to customers around the BP as part of the A&A testing but these hadn’t been brought to the full meeting. It was important to see how the plan was changing as a result of customer engagement so far. | As the Business Plan evolved, members of the ICG were able to see drafts of the Executive Summary and developing Business Plan content from June to September 2023 | ICG meeting 15 September 2023 | Closed
135 | Customer engagement | 16 June 2023 ICG meeting | Challenge/question | How was AW going to feed back to customers the level of change in the Business Plan following customer feedback? How had this influenced business decisions? It was important to build relationships with customers | AW took this away as an action point. A CRM was in development Addressed in Your Water Your Say session and via the business plan |  | Open
136 | Customer engagement | 16 June 2023 ICG meeting | Challenge/question | Members asked whether they could see the Customer Advisory Board challenge log/minutes and Craig would attend one CAB meeting each year | The challenge log was shared with ICG ahead of the 15 September ICG meeting | 2023-08-01 | Closed
130 | Affordability & Acceptability Testing | 5 May 2023 Task and Finish Group | Challenge/question | Members asked whether regulators had seen alternative BP proposals before this was shared with customers | A full customer engagement update and BP overview was dicussed at the ICG meeting on 16 June 2023. Full T&F group invited to comment on A&A Quant survey on 20 June 2023 | ICG meeting 16 June 2023 | Closed
112 | Customer engagement/gamification | 8 Feb 2023 Task and Finish Group | Challenge/question | Was gamification the best way to measure trade offs (also a related question at 14 March Task and Finish Group) | Customer preferences would be triangulated in the context of other qualitative engagement to gather a blend of views. (Gamification research was halted - briefing note to ICG members 2nd June. BP presented to ICG on 16th June.) | ICG meeting 16 June 2023 | Closed
113 | Customer engagement/segmentation | 14 March 2023 Task and Finish Group | Challenge | Members had noticed an imbalance in terms of gender and age range on the online community (more skewed towards male and older members), which is not necessarily reflective of AW customer base. | In an ideal world, it would be nice to have equal balance across segments and equal segmentation. But the online community plays a role as one part of a wider engagement programme. The online community is a first port of call and a testing ground. AW’s mixed method approach to customer engagement means that each approach serves different individual purposes and together these cover all the bases. | 14 March 2023 Task and Finish Group | Closed
115 | Customer engagement/NHH | 14 March 2023 Task and Finish Group | Challenge/question | How would AW decide whether an NHH sample is representative? With a wide range of users, could stakeholders such as NFU be engaged? | Current focus was on the qualitative rather than quant stage, but AW would give careful consideration when they get to that stage to make sure everyone’s voices are heard. | 14 March 2023 Task and Finish Group | Closed
116 | Customer engagement/NHH | 14 March 2023 Task and Finish Group | Challenge/question | How does AW weight different users of water? Are users all treated as equal or weighted according to size? | Feedback would be taken on board at the quantitative stage. | 14 March 2023 Task and Finish Group | Closed
117 | Customer engagement/ICG role | 14 March 2023 Task and Finish Group | Challenge | What's put in front of customers about the BP is a really significant part of the process and it’s important that the wider ICG should see that and that it should be reviewed carefully. The way it’s presented could be handled by the Task and Finish Group but the content of the plan is an important issue for the broader ICG. | AW is approaching this in line with Ofwat’s guidance – to demonstrate and present that information in a way that’s easy for customers to understand. The agenda for the March ICG meeting would help to inform that; this will include looking more at how AW has come to decisions, looking at long list of PCs and how customer engagement has informed the more refined list. (UPDATE: Item was covered at 16th June meeting. All members invited to review draft Quantitative questionnaire before fieldwork. Including where areas of the guidance have been supplemented with additional information. Evidence of how customer insight informed business decisions presented to group 16th June.) | ICG meeting 16 June 2023 | Closed
118 | Customer engagement/segmentation | 14 March 2023 Task and Finish Group | Challenge/question | Shouldn't customer engagement be more heavily weighted towards dual supply customers? | In terms of Ofwat guidance, AW isn’t obliged to carry out any customer engagement work with Hartlepool but they recognise these customers as being important so are planning to conduct research there. The rest of the splits are led by Ofwat’s guidance. | 14 March 2023 Task and Finish Group | Closed
121 | Customer engagement/gamification/vulnerable customers | 14 March 2023 Task and Finish Group | Challenge/question | Would customers be given choices about social tariffs and cross subsidies in the gamification platform? | AW discussed this and decided this wasn’t the best platform to generate this insight. | 14 March 2023 Task and Finish Group | Closed
122 | Customer engagement/ICG role | 14 March 2023 Task and Finish Group | Challenge/question | How would the comments of the Task and finish Group on customer engagement materials be addressed? | AW had been responding to comments individually and suggested members of the group would need to go back into materials and make sure they’re responded to. However, she would make any changes clearer in future. | 14 March 2023 Task and Finish 2022 Group | Closed
109 | Customer engagement/Acceptability and Affordability Testing | Task and Finish Group | Challenge/question | Is AW planning to share only two versions of the Business Plan with customers as part of Affordability and Acceptability testing – and, if so, what is the difference in monetary impact between the two? | AW was just looking at 2 options of the Business Plan at the moment. For AW, the ‘must do’ version is not necessarily the least cost option. Bill impacts are being modelled and this will be quite clear as part of the one-page summaries shared with customers. Within the qualitative phase, AW is going over and above what’s prescribed in Ofwat/CCW guidance in terms of number of groups spoken to, with particular focus on intergenerational fairness. | Task and Finish Group | Closed
110 | Customer engagement/Acceptability and Affordability Testing | 8 Feb 2023 Task and Finish Group | Challenge/question | How would interviews for Affordability and Acceptability Testing be carried out to guarantee accessibility? | There would be a mixture of media used; the main deliberative events would be 4.5 hours long, interactive, with breakout and plenary sessions to ensure everyone is engaged. There would then be 16 in-depth interviews with people on the Priority Services Register (PSR) or eligible to be on the PSR. Accent would make sure they are carrying out interviews in the preferred way for the customers (either in person or online). Social tariff interviews would be done digitally. Intergenerational family groups are one of additional elements not included in guidance. There would be “Sunday dinner conversations” with different generations from one family, held in the family home. NHH interviews would be done digitally (for business audience). There would be one event held for customers in Hartlepool (even though this was not a requirement). Two events would also be held in dual supply areas (Essex and Suffolk). | ICG Meeting 16 June 2023 | Closed
111 | Customer engagement/Acceptability and Affordability Testing | 8 Feb 2023 Task and Finish Group | Challenge/question | The NHH figure of 200 seemed quite low - was there any opportunity to increase that? What % of customers would be involved in Hartlepool, Essex, Sussex etc? | Yes, we will have minimum of 200 NHH in Quant and will be promoted through existing channels to increase this sample. | ICG meeting 16 June 2023 | Closed
101 | Customer engagement/Acceptability and Affordability Testing | 20 Jan 2023 ICG meeting | Challenge | How is AW going to respond to Ofwat’s guidance on Affordability and Acceptability Testing? | Addressed through agenda item at January 2023 ICG meeting. Concerns also addressed at 16 June ICG meeting, then all members will be able to review draft Quantitative questionnaire before fieldwork. | ICG meeting 16 June 2023 | Closed
102 | Customer engagement/Acceptability and Affordability Testing | 20 Jan 2023 ICG meeting | Challenge | Concerns were expressed that AW was presenting only a "must do" and preferred version of the business plan to customers as part of the AA Testing rather than 3 versions. It was felt this didn't give enough choice. | Answer at ICG meeting: AW was responding to Ofwat requirements but clearly the company view would be informed by a wealth of detail gathered from customer engagement. The task before AW is that they articulate the company plan without unnecessarily “leading the witness”. | ICG meeting 20 Jan 2023 | Closed
88 | Customer engagement | 11 Jan 2023 Task and Finish Group | Challenge/question | Members would like to see any final customer engagement materials and how their comments had been incorporated. | Ongoing. Responses to members comments being recorded directly on materials to ensure line of sight between comments and responses. |  | Closed
89 | Customer engagement | 11 Jan 2023 Task and Finish Group | Challenge/question | Members would like to go along to pilot testings and customer engagement sessions. | We have had limited in person and focus groups compare to PR19 due to changes in the way the engagement programme is being delivered and focusing on 'quality rather the quantity engagement' as per the Ofwat guidance. Recordings of focus groups as part of knowledge hub are available for viewing. | Written response | Closed
90 | Customer engagement | 11 Jan 2023 Task and Finish Group | Challenge/question | Members would like to see questions for online community and be able to log into the community. | Online community activities can be viewed with the log on details provided and can be viewed even after the events have closed. Log of all activities are included in the Synthesis report and referenced accordingly with all reports (including those done for our everyday insight - not just for PR24) saved in the reports folder | 2023-01-01 | Closed
91 | Customer engagement | 11 Jan 2023 Task and Finish Group | Challenge/question | Members would like information on sample sizes and segmentation | Standard segmentation strategy was shared |  | Closed
92 | Customer engagement | 11 Jan 2023 Task and Finish Group | Challenge/question | Members asked for the company to be clear in the materials circulated for review which parts were prescribed and which were company specific (bespoke), as this would make it easier for the group to review |  |  | Closed
95 | Customer engagement | Email 23/12/22 | Challenge | What has changed as a result of listening to customer feedback? | Synthesis report presented at multiple meetings in line with Quarterly updates. Details on how insight used to inform busiess decisions presented at 16 June ICG meeting. | ICG meeting 16 June 2023 | Closed
96 | Customer engagement/vulnerable customers | Email 23/12/22 | Challenge | How are AW approaching the traditional hard to reach groups? | Differences drawn out in Synthesis report under heading 'are there any differences to be aware of'. Also explicitly drawn out in June 23 version. | 2023-06-01 | Closed
97 | Customer engagement | Email 23/12/22 | Challenge | How is AW balancing customer priorities over profit (i.e. long versus short term rewards?) | Demonstrated through the business plan narrative, balancing deliverability, affordability and financeability |  | Open
98 | Customer engagement | Email 23/12/22 | Challenge/question | What is the make up of the AW Board and what are the discussions at the Board level about customer priorities? How is the customer voice represented at the Board level? | https://www.anglianwater.co.uk/about-us/who-we-are/group-structure/our-board/ Some Board members attended PR24 customer engagement events and as well as attending the June 2023 ICG meeting. Chair of ICG attended Board in July 2023 |  | Open
85 | Societal valuation | 9 Dec 2022 ICG meeting | Challenge/information | ICG members were interested in seeing Ofwat's values and how these differed from AW's values. | AW agreed to add this to a future agenda. Report available as links from synthesis report. Triangulation covered by ICS at 16 June meeting. Ofwat and AW values also dicussed at 16 June meeting. | 16 June ICG meeting | Closed
56 | Customer engagement/customer principles | 6 Oct ICG 2022 meeting | Challenge/information | How would customer principles be interpreted in a way that’s clear and fair? | A big part of programme was being able to demonstrate multi-method approaches, using business as usual channels first. There is flexibility to change the customer principles and refine them through the price review process. | 6 Oct ICG meeting | Closed
57 | Customer engagement/Synthesis report | 6 Oct 2022 ICG meeting | Challenge/information | Would it be possible to add a box at bottom of each page of the synthesis report to show how customer engagement has informed decisions. | AW suggested this was to be considered. We continued to review and develop the synthesis report |  | Open
50 | Customer engagement | 2 Sept 2022 ICG meeting | Challenge/information | Members felt they would like to see more info on customer engagement generally. | Addressed through agenda and pre-reading for 6 October 2022 meeting. Update on all activities and workstreams and how ICG have been involved presented at 16 June meeting. |  | Closed
31 | Customer engagement/role of ICG | 18 July 2022 ICG meeting | Challenge/information | What was ICG’s assurance role? | Response: AW was keen to map out assurance in more detail and ICG would be involved in evaluation stage. | ICG meeting 18 July 2022 | Closed
30 | Customer engagement/customer principles | 18 July 2022 ICG meeting | Challenge/information | How did AW’s CE principles map into Ofwat and CCW principles? | Response: AW had rolled 8 of Ofwat’s objectives together and made them more tailored for AW. She was comfortable that these are the best focus for AW, drawing on good practice across the sector. Golden thread between CE and business plan would be more evident and obvious. | ICG Meeting 18 July 2022 | Closed
32 | Customer engagement/online community | 18 July 2022 ICG meeting | Challenge/information | How representative is the online community for the AW customer base? | Response: AW were looking at membership of online community and would be looking to have a specific PR24 group, drawing on informed and uninformed customers. Online community has been refreshed twice since October 21 through various channels. Acknowledge filling some quotas has been difficult. | ICG Meeting 18 July 2022 | Closed
33 | Customer engagement | 18 July 2022 ICG meeting | Challenge/information | Was there anything that hadn’t been included in terms of customer engagement for PR24? | Response: AW would have lower presence on the ground in terms of CE for PR24 but would focus on where they can make a difference. Low pressure area not covered in synthesis report due to lack of insight but not deemed to be a significant issue to take forward into PR24 so no further research conducted. | ICG Meeting 18 July 2022 | Closed
35 | Triangulation/Business as usual data | 18 July 2022 ICG meeting | Challenge/information | Members asked about “rebalancing use of everyday research” and use of BAU data. | Response: this information would all be pulled into the synthesis report. | ICG meeting 18 July 2022 | Closed
8 | Triangulation/Business as usual data | 21 Dec 2021 CEF meeting | Challenge | How would AW be taking BAU data forward to get a more rounded picture of customer views? | Response: it was early days in the process but AW were looking to build on what already existed and identify any gaps. | CEF Meeting 21 Dec 2021 | Closed
44 | Customer engagement/customer principles | Email 20 July 2022 | Challenge | ICG members felt that the various planning and delivering activities for customer engagement that Anglian outlined seemed quite comprehensive. We liked the proposed development of ‘Customer Principles’ and welcome the introduction of the ‘scoring card’ for the synthesis report. Our query relates to ‘Capturing everyday insight’ at Step 2. The sources of ‘everyday insight’ that are listed all seem to revolve around uninformed views. While this data is useful, it must be balanced carefully with informed views and, arguably, the latter should be given more weight. This is especially crucial for issues that customers have been particularly uninformed about, such as the environment. Otherwise, there is a risk that the process will be skewed towards approving actions that might not actually tackle the main problems. | Uninformed customers recruited for new online community under title of Knowledge Hub - activities and focus groups conducted with this group to ensure this group is included. |  | Open
29 | Customer engagement/customer segmentation | 18 July 2022 ICG meeting | Challenge/information | Were AW using the same customer segmentation as PR19 and how would they pull future customers into engagement? | Decision taken not to do behavioural segmentation at PR24. Segmentation strategy is the standard we have been using across all relevant material. | ICG meeting 18 July 2022 | Closed
1 | Triangulation | 19 March 2021 CEF Meeting | Challenge | On willingness to pay on ODIs: AW could have done more by looking at other companies' studies. This could be taken on board for future price reviews. | Response: AW is considering how to make triangulation evidence more useful and accessible to show how it helped to shape AW business planning, including through the synthesis report. | ICG meeting 16 June 2023 | Closed
6 | Triangulation | 13 July 2021 CEF Meeting | Challenge | Would triangulation (which was a welcome development in PR19 and AW did well) fall by the wayside in PR19 with the move towards national research? | Response: AW planned to retain triangulation to help shape future plans and decisions. | ICG meeting 16 June 2023 | Closed
Synthesis Report
103 | Customer engagement/Synthesis report | 20 Jan 2023 ICG meeting | Challenge | ICG members were pleased to see their comments had been integrated in the Synthesis report but had a few outstanding questions: members wanted to see clickable links to source papers and also wanted to see links to societal valuation work | Clickable links now provided in March 2023 report onwards. Societal valuation included in synthesis report and reports linked acordingly. (Note: not all ICG members were able to access the links) | 2023-03-01 | Closed
93 | Customer engagement/synthesis report | 11 Jan 2023 Task and Finish Group | Challenge/question | Members would like access to the customer engagement materials that had informed the reports/fed into the synthesis report. They would also like to see which information was new. | With regards to referencing we’re in the process of trying to set up a resource library on the website where all of these reports will sit. We can then use this to hyperlink link out of the synthesis report to the actual data sources which will be great for clarity and transparency. Plan is to have this complete for the next iteration. | 11 Jan 2023 Task and Finish Group | Closed
68 | Customer engagement/Synthesis report | Email 10 Oct 2022 | Challenge | Scoring: not a clear mapping to validity and reliability. More specifically, expect to see something relating to whether the research is local, regional or national, and some score given depending on how long ago the research was conducted. Also, sample size, whether representative, whether hard-to-reach groups are included. | Claire has added whether the research is local, regional or national in the reference box at the end of the document as well as more information on sample size and scoring given. | AW email 13 Jan 2023 | Closed
25 | Customer engagement/Synthesis report | Email shared at ICG meeting 10 May 2022 | Challenge/information | Members wanted to look at the synthesis report and input on how it could be improved (if at all) at the outset | Item on agenda October 2022 | Closed (agenda item in October ICG meeting) | Closed
28 | Customer engagement/synthesis report | 18 July 2022 ICG meeting | Challenge/information | How would centralised research connect with local research and how would it be balanced/weighted? | Response: the centralised research would feed into the synthesis report and views would be balanced. | ICG Meeting 18 July 2022 | Closed
| Customer engagement/Synthesis report | 6 Oct 2022 ICG meeting | Challenge | The sum of scores is implied a meaning as a summary measure by the fact it is the one metric included alongside each of the findings. This is ok, albeit bearing in mind that something is always going to be lost when presenting summary info. However, something is needed in the intro to guide interpretation of the meaning of overall scores. For example, could there be a RAG rating re confidence associated with each aggregate score band, plus some caution re the problem with aggregating generally? | Claire has refreshed the scoring methodology and added in the RAG status, as suggested. We have also updated the front sections to explain the methodology further. | AW email 13 Jan | Closed
| Customer engagement/Synthesis report | 6 Oct 2022 ICG meeting | Challenge | On format throughout doc, could be helpful to sort insights by score. | When Claire has added new insight for this version she has put it in green and then reflected it in ‘what does the majority of insight suggest’. In the next version this text will turn that black and any new insight will go green to demonstrate what has come in since last version. | AW email 13 Jan | Closed
| Customer engagement/Synthesis report | 6 Oct 2022 ICG meeting | Challenge | Can new questions be added as become important? At the moment, they’re quite high level whereas it will be important to be able to assess whether the evidence supports decisions made in the plan. For example, the WRMP will be delaying environmental destination. Is this supported by customer evidence? More generally, it will be good to have the flexibility to add specific questions for future iterations. | Yes, we have tightened up some of the questions for this report as our thinking emerges and open to change as we move forward. | AW email 13 Jan | Closed
| Customer engagement/Synthesis report | 6 Oct 2022 ICG meeting | Challenge | Relatedly, there is a question around how this will be combined with CBA model results, which permeates quite a few areas. | Approach to triangulation covered at 16 June meeting. | ICG meeting 16 June 2023 | Closed
36 | Customer engagement/Synthesis report | 18 July 2022 ICG meeting | Challenge/information | How would the loop would be closed between the customer engagement principles document and the synthesis report and how the insights had helped inform decision making? | Response: it would be helpful to sense check with customers that AW’s understanding about what they had said was correct at the business planning stage. | ICG Meeting 18 July 2022 | Closed
37 | Customer engagment/Synthesis report | 18 July 2022 ICG meeting | Challenge/information | Members would like to see the Synthesis report every quarter |  |  | Closed
7 | Customer engagement/Synthesis report | 21 Dec 2021 CEF meeting | Action/information | CEF members asked for an update on the synthesis report that was used in PR19, as well as updates on WRMP and DWMP research. | Response: AW planned to turn the synthesis document into a regularly updated and interactive document. | CEF Meeting 21 Dec 2021 | Closed
DWMP (published 31 May)/pollution incidents
158 | PIRP | 15 September 2023 ICG meeting | Challenge | In light of deviating from Ofwat metrics on pollution incidents, was AW confident of meeting targets on reducing incidents? | AW was confident in delivering PC levels and delivering on zero pollution incidents as soon as possible. It would continue to engage with the ICG on this = there was no diminution of intent through change in incentive rates. |  | Ongoing
159 | PIRP | 15 September 2023 ICG meeting | Challenge | ICG members felt that PIRP plans should come through more clearly in the Executive Summary of the Business Plan as this was such a strong focus for the public. | AW would take this suggestion away. |  | Pending
150 | PIRP | 25 July 2023 ICG meeting | Challenge | ICG members applauded the PIRP ambition, but pointed out that AW couldn’t tackle this alone. ICG would like to see a step change towards zero pollution incidents and were surprised that some of the thinking about the PIRP hadn't landed earlier. Members also suggested that AW and other water companies could play a more significant role in advocacy | AW colleagues reiterated their commitment to reducing pollution and partnership working was key for this - but there was acknowledgement that there needed to be a step change improvement |  | Open
105 | CSOs | 20 Jan 2023 ICG meeting | Challenge | The ICG would like to see a clear glide path in terms of CSOs | Answer at ICG meeting: this would be made very clear in the narrative. | 20 Jan 2023 ICG meeting | Closed
106 | CSOs | 20 Jan 2023 ICG meeting | Challenge | Members wanted to make sure there was a clearer link for the customer between investments to tackle issues like CSOs and bill impacts. Communications of what bills would buy for customers was key | We did not complete a separate bill impact exercise for the DWMP. Bill impact work is being completed as part of the LTDS and PR24 and will be shared in due course. | 15 September 2023 ICG meeting | Closed
100 | Pollution incidents/customer trust | 20 Jan 2023 ICG meeting | Challenge | What did AW hope to do to restore trust in the company around pollution incidents? What are the number now? | Answer at ICG meeting: The number hadn’t changed since December: 7 incidents in first six months and 3 in last part of year. AW’s ambition is to not have any serious pollution incidents, which is the best way to restore trust. Initiatives such as River Positive are important too. | 20 Jan 2023 ICG meeting | Closed
99 | Pollution incidents/performance | 20 Jan 2023 ICG meeting | Challenge/question | Questions were asked about the £500k fine for pollution incident in 2017 reported in the media. | Answer at ICG meeting: Two independent alarm systems had failed at a terminal pumping station. On a routine inspection, a technician visited the site 23 hours later, noted the problem and reported it. AW faced strict liability for the offences. It was regrettable and wasn’t done intentionally. PS said AW took lessons learned and made sure similar circumstances couldn’t happen. | 20 Jan 2023 ICG 2022 meeting | Closed
94 | DWMP/Storm overflows | Email 29/12/22 | Challenge | Will Anglian Water’s DWMP be fully compliant with the government’s Storm Overflows Reduction Plan (SORP)? AW has made public commitments to reduce storm overflows to an average of 20 per year by 2025 and to ‘ensure storm overflows and sewage treatment works do not harm rivers by 2030’ but they must ensure that they are compliant with all aspects of the SORP in line with the legislation. | Response from company by email 4/1/23: Happy to discuss more when we meet but yes I can confirm that the DWMP will be fully compliant with the SORP. Included in January meeting agenda. | Email 4/1/23 | Closed
83 | Pollution incidents/performance | 9 Dec 2022 ICG meeting | Challenge | Is zero pollution incidents achievable? What is the glide path for following years for pollution incidents | Updates to be brought back to ICG in March and June/July 2023 and outlined within the LTDS | 25 July 2023 ICG meeting | Closed
84 | WRMP/Pollution incidents/performance | 9 Dec 2022 ICG meeting | Challenge | There were a lot of reputational issues for AW around pollution incidents. How were they going to improve their reputation with customers? | Response from company at ICG meeting: there is a mass of things AW is doing around environmental improvements; e.g. commitment to Get River Positive. AW is working hard to showcase other amazing work being done, for example, through the advanced WINEP. AW is the first company to publish an interactive map to show latest investment schemes to improve the environment, 2021 storm overflow data (also known as Combined Sewer Overflows) and river network. | 25 July 2023 ICG meeting | Closed
80 | Pollution incidents/performance | Emails 25/10 & 27/10 2022 | Challenge/information | How is the company progressing with the implementation of their Pollution Incident Reduction Plan and how is this influencing both current performance and future environmental ambition as we move towards PR24? | Added to December agenda, addressed in pre-reading materials | 25 July 2023 ICG meeting | Closed
63 | Drainage and Wastewater Plan | 6 Oct ICG meeting | Challenge/information | It wasn't clear to members how customer preferences have been factored in. Members also wanted to know how DWMP, WRMP and other plans were being joined up - and wanted to see more info on storm drains | Response: teams had been talking to each other to make sure plans were joined up. They were intrinsically linked – using the same PCC numbers and growth forecasts. More details on storm drains to come to December meeting. Customer preference was included within AW's Best Value Planning assessment as a weighted score for solutions. This outlined in sections 4.8 and 6 of our technical document https://www.anglianwater.co.uk/siteassets/household/about-us/dwmp/dwmp---technical-report-1.pdf | 6 Oct ICG meeting | Closed
47 | Drainage and Wastewater Plan | Email on 20 July 2022 | Challenge | To build on the comments above, it felt as though the DWMP had been constructed within a slightly different/separate bubble and it wasn’t entirely clear how this read across to the PR24 and WRMP processes. We felt this needed to be clarified. | Addressed through agenda and pre-reading for 6 October meeting (Subsequent update in June 2023: The DWMP and WRMP are aligned in their base data used. The DWMP will differ from PR24 as we have taken wider business needs and affordability into consideration. Narrative and commentary will go alongside the business plan to demonstrate the line of sight from DWMP to LTDS and PR24.) | 6 Oct ICG meeting and written response in June 2023 | Open
41 | Drainage and Wastewater Management Plan | 18 July 2022 ICG meeting | Challenge/information | Members wanted to see more details about cost-benefit analysis | Response: PR19 information had been used but AW will bring weighting through to PR24. This is outlined in section 6 of our technical document https://www.anglianwater.co.uk/siteassets/household/about-us/dwmp/dwmp---technical-report-1.pdf | ICG Meeting 18 July 2022 and written response June 2023 | Closed
10 | Pollution incidents | 21 Dec 2021 CEF Meeting | Challenge/information | Were pollution incidents since Jan/Feb going in the right direction? | Response: Pollution incidents were quite volatile and it was hard to see a trend. However, AW had an incident reduction plan in place with multiple initiatives. | ICG meeting 25 July 2023 | Closed
Hartlepool
150 | Bill profile/Hartlepool | 30 June 2023 ICG meeting | Challenge | ICG member raised the question of considering different tariff levels for Hartlepool to address customers’ desire for lower bills. | Tariffs were already different for Hartlepool. In the PR19 period, when there wasn’t much proposed investment for Hartlepool, the decision was made to suppress their bill increase. It was seen as more of a targeted, one-off adjustment. In the PR09 and PR14 periods, significant upgrades were carried out in the Hartlepool region. The aim now is to bring everything back on track in terms of broad cross-subsidy. | ICG meeting 30 June 2023 | Closed
137 | Customer engagement/Hartlepool | 16 June 2023 ICG meeting | Challenge | More information about customer engagement in Hartlepool was requested | This was covered at the 30 June ICG meeting | ICG meeting 30 June 2023 | Closed
114 | Customer engagement/Hartlepool | 14 March 2023 Task and Finish Group | Challenge | Although Hartlepool is covered in the engagement, there didn’t seem to be anyone from Hartlepool involved in tasks on the online community. | Online community has been refreshed twice during development of PR24. There are a handful of Hartlepool members in the community but recruiting them has been difficult. Due to nature of the activity being voluntary can't always guarantee they take part. Hartlepool represent 1% of population so representative views will always be small. | 14 March 2023 Task and Finish Group | Closed
9 | Hartlepool/online community | 21 Dec 2021 CEF Meeting | Information | Did Hartlepool customers feature in the online community? | Response: There was a specific focus on Hartlepool customers in the online community. AW were also looking at face to face interview with customers in Hartlepool, who would be included and represented in research. | CEF Meeting 21 Dec 2021 | Closed
LTDS
81 | Customer engagement/LTDS | 9 Dec 2022 ICG meeting | Challenge/information | How would customer engagement on the Water Resource Management Plan (WRMP) and other strategies be used for the LTDS. | Response from company at ICG meeting: AW is taking that as a starting point and retesting insights gathered previously. This information is gathered together in the synthesis report | ICG meeting 9 Dec 2022 | Closed
82 | Customer engagement/LTDS | 9 Dec 2022 ICG meeting | Challenge/information | The ICG would be interested in getting more information about the customer engagement around LTDS. Would like to see briefing for customers of different scenarios at the January ICG meeting. | Added to January 2023 agenda. Update of all activities in June 2023 meeting pack. Many activities generated insight for both AMP8 and LTDS together. | 30 June 2023 ICG meeting | Closed
83 | LTDS | 9 Dec 2022 ICG meeting | Challenge | 25 years doesn’t feel very long term. Should we be looking further out, due to increasing changes to the climate? | Response from company at ICG meeting: responded that Ofwat data requirements are for 25-year look but that sits within longer term strategic direction. | 9 Dec ICG meeting | Closed
69 | LTDS/Sustainbility/resilience/climate change | Email 25/10/2022 | Challenge/information | How is AW planning to improve asset resilience, both generally and in light of more extreme weather and climate change? | Added to December 2022 agenda, addressed in pre-reading materials. Written response from AW in June 2023: There are many different facets to the question of resilience (e.g. operational resilience, financial resilience, and the long-term resilience of our services in the face of growth and climate change). At PR19 we created a resilience strategy that considered all of these elements in the round. We have reviewed this strategy for AMP8 and for LTDS. In our LTDS we have tested investments against a series of scenarios (including climate change and growth) to ensure we are prepared for a range of plausible futures. An example of this is the investment for climate vulnerable mains. We are also thinking about the interdepencies between our assets and other networks, for example UK Power Networks and BT. We are working across sectors to understand these dependencies and to work together to find the most efficient solutions. | 9 Dec ICG meeting | Closed
70 | LTDS/Sustainbility/resilience/growth | Email 25/10/2022 | Challenge/information | What is AW strategy to enable growth in areas of nutrient and/or water neutrality? | Added to December agenda, addressed in pre-reading materials | 9 Dec ICG meeting | Closed
58 | LTDS/Demand management/sustainability | 6 Oct 2022 ICG meeting | Challenge/information | · Is AW doing enough to promote efficient use of water and per capita water reduction? | Addressed through agenda and pre-reading for 6 October meeting | 6 Oct ICG meeting | Closed
59 | LTDS/Demand management/sustainability | 6 Oct 2022 ICG meeting | Challenge/information | · What customer engagement has AW engaged in regarding spend on reservoirs? | On agenda for December meeting | 9 Dec ICG meeting | Closed
60 | LTDS/Demand management/sustainability | 6 Oct 2022 ICG meeting | Challenge/information | · How is AW engaging in community engagement around reservoir locations? | On agenda for December meeting | 9 Dec ICG meeting | Closed
61 | LTDS/Demand management/sustainability | 6 Oct 2022 ICG meeting | Challenge/information | · How has AW engaged with customers in debates and dilemmas around security of supply? | Addressed through agenda and pre-reading for 6 October meeting | 6 Oct ICG meeting | Closed
62 | LTDS/Demand management/sustainability | 6 Oct 2022 ICG meeting | Challenge/information | Members would like to see the evidence to prove the causal link between metering/Love Every Drop and the region’s behaviour (see point 49) | Addressed in 30 June ICG meeting | 30 June 2023 ICG meeting | Closed
63 | LTDS/Demand management/sustainability | 6 Oct 2022 ICG meeting | Challenge/information | One of the key trade offs is how quickly AW reaches environmental destination. With that in mind, when will the decision be made about bringing in desalination, which is unpopular with customers. | AW is looking at a combined reservoir/desalination option. Desal might be quicker to deliver but it’s not the silver bullet. AW wants to focus on reservoirs, which is supported by customers. Desal is expensive in terms of costs and environment and there are important water quality considerations. Maximum blend would be 50/50. | 9 Dec ICG meeting | Closed
55 | Long-term delivery strategy Willingness to Pay | 6 Oct 2022 ICG meeting | Challenge/information | Was any planning being done to make sure that different Best Value Plans were taking into account what customers were willing to pay when taken in the round. | Response: all direction is taken from the Long Term Development Strategy, which is where the company articulates how everything comes together. | 6 Oct 2022 ICG meeting | Closed
54 | Long-term delivery strategy Sustainability/climate change | 2 Sept 2022 ICG only meeting | Challenge/information | Members would like to challenge the company around operating practices and environmental practice in the face of climate change. | Heard from Allan Simpson who lead development of LTDS in September 2023 |  | Open
52 | Long-term delivery strategy Reservoirs | 2 Sept ICG only meeting | Challenge/information | Members would also like to know more about plans to communicate about the reservoirs/need for the reservoirs with customers. What are contingency plans if these don’t come on line quickly enough to provide water for the region | Response at December ICG: There could be delays but there are things that could be sped up (e.g. putting water in to reservoirs more quickly). Going further in demand is relevant here – even with full smart meter roll out, there’s so much more to do. There’s also making sure government plays role (e.g. around labelling and efficiency of white goods) as well as piloting of water reuse and desalination. | 2 Sept ICG only meeting | Closed
53 | Long-term delivery strategy Sustainability | 2 Sept 2022 ICG only meeting | Challenge/information | Members wanted to see information about assumptions around baseline flows and sustainable abstraction. | We have been liaising with the Environment Agency and Natural England on sustainable abstraction. Please refer to the Sustainable Abstraction and Environment report, Decision Making report and Supply Forecast report in the challenge log folder. | 2 Sept 2022 ICG only meeting | Closed
51 | Long-term delivery strategy Resilience/sustainability | 2 Sept 2022 ICG only meeting | Challenge/information | Members would like to see demonstration of how AW is using resources and educating customers on water use. | Addressed through agenda and pre-reading for 6 October meeting | ICG meeting June 2023 | Closed
49 | Long-term delivery strategy Sustainability/resilience | Email 5 Sept 2022 | Challenge | East Anglia is one of the driest parts of the country and this summer has been particular for the lack of rainfall. AW are planning new reservoir capacity but this will not come on line for a number of years. The whole of the east of England moved into official drought status on 12th August but no significant moves to limit water use have been made by AW. How is AW weighing up all of this with the short term requirements for adequate water for the any new homes being built across the area, and is there not a case for more significant moves to reduce demand? | Addressed through agenda and pre-reading for 6 October meeting. Customer behaviour in AW region was different from other regions across the UK - in part due to smart meter roll out and Love Every Drop messaging. | 6 Oct 2022 ICG meeting and 30 June 2023 | Closed
46 | Long-term delivery strategy/Reservoirs | Email on 20 July 2022 | Challenge | Decision on reservoirs. In the slides, we couldn’t actually see a clear line of sight between the statement in section 9.5, ‘Our customers want us to ensure we have a low impact on the environment’, and the decision that reservoirs were the best way to do this. We were also a little puzzled that water re-use seems fairly low profile in the plans, even though it was popular with customers and is arguably friendlier to the environment than building reservoirs. In particular, water re-use needs to be explained, very transparently, right from the start. How does the reference to 600 catchments for water re-use in the DWMP fit in with the references to water re-use in the WRMP? | We have explained our options in the following WRMP24 reports: Demand Management Options Appraisal, Demand Management Options Preferred Plan and Supply-side options. Evidence was provided on the environmental benefits of the reservoirs at the ICG in December 2022. Water reuse in the areas we are looking at will require membrane technology, similar to desalination, so will be high in operational carbon. It will also involve the production of brine which has to be safely disposed of, to ensure no environmental impacts. Taking the final effluent away from a watercourse could also have environmental considerations. Water reuse is also limited by the dry weather flow of the Water Recycling Centre. | Written response June 2023 | Closed
22 | Long-term delivery strategy Resilience/growth | Email shared at ICG meeting 10 May 2022 | Challenge/information | What is the company's role when it comes to balancing growth and the environment (e.g. nutrient neutrality, water demand neutrality, carbon neutrality) | This was agreed as a good future agenda topic. Written response June 2023: Balancing growth against the impacts on the environment is the role of government. AWS role is to enable that growth and to play our part to make that growth possible in the most sustainable way. E.g. in WRMP we have to use Local Authority plans to develop our growth forecasts. We also have to consider the sustainability of our abstractions and to find the 'best value' solution that enables growth shilist protecting and enhancing the environment. Head of Sustainable Growth will attend meeting 25 January 2024 to discus how company responding to growth | Email shared at ICG meeting 10 May 2022 | Open
21 | Long-term delivery strategy Resilience/smart meters | Email shared at ICG meeting 10 May 2022 | Challenge/information | How is the company planning to realise the benefits of its smart meter role out in terms of enhancing the customer relationship and on reducing water use/value of water | his was previously discussed in the December 2022 meeting. It will also be part of the June 2023 reading. | June 2023 ICG meeting | Closed
22 | Long-term delivery strategy Resilience/water efficiency | 10 May 2022 ICG meeting | Challenge/information | How are customers being engaged around water use/water efficiency? | Response: in every interaction with customers over leakage, the team recommends water saving measures and tailor future communications accordingly. | June 2023 ICG meeting | Closed
24 | Long-term delivery strategy/reservoirs | Email shared at ICG meeting 10 May 2022 | Challenge/information | Members wanted to look at customer engagement around the two reservoir proposals | Item on agenda October and December 2022 ICG meeting | December 2022 ICG meeting | Closed
26 | Long-term delivery strategy/Resilience | 18 July 2022 ICG meeting | Challenge/information | Members asked about the asset resilience of water supply in the face of climate change, particularly when potentially facing a prolonged period of drought. Was there too much abstraction at this time? | Response: the level of stress on assets on top of extreme weather events was enormous and was set to become the norm rather than the exception. If the water industry continues on its current trajectory, the company will be underinvesting. Ofwat recognises some change may be needed in this regard. The water industry needs to look at capital investment. AW was not in an over-abstraction position. Reservoirs were around 89% full. AW would liaise with EA if the situation changed. | ICG Meeting 18 July 2022 | Closed
39 | Long-term delivery strategy/Sustainability | 18 July 2022 ICG meeting | Challenge/information | How were sustainable levels of water measured? | Response: when AW talks about surplus, they are talking about surplus in supply-demand balance. Customer have said they value the best environments so AW wants to protect those as soon as possible, going down to individual abstraction levels. As surplus water comes online, AW can then make choices about the water that’s available to them. (Written response June 2023: Sustainable levels of water abstraction have been agreed with the Environment Agency and used in our models. We monitor these abstractions all the time. Please refer to the reading in the challenge log folder: Supply Forecast report and Sustainable Abstraction and Environment report.) | ICG meeting 18 July 2022 | Closed
48 | Long-term delivery strategy/Sustainability/resilience | Email 1 Sept 2022 | Challenge | We would be keen to understand why AW have not implemented any sustainable water use restrictions (i.e. hosepipe bans) given the region is in a drought which could stretch into next year and get a lot worse if we don't have above average rain. The measures taken by other companies are reducing demand by around 5-10%. While AW may have enough water stored for public water supply needs, they should also be thinking about the environment and other water users...using less now means abstracting less next year and leaving more for farmers and the environment. This approach seems to undermine the need for two new reservoirs | Addressed through agenda and pre-reading for 6 October meeting (Written update June 2023: Our PCC was at a record low last year. We were able to help agricultural stakeholders with additional water, as well as inputting further water into the environment.) | 6 Oct ICG meeting and written response in June 2023 | Closed
16 | Long-term delivery strategy | 10 May 2022 ICG meeting | Challenge/information | Is there any general information about customer input/preference around LTDS? | Response: there are customer preference features at different parts of the plan and there will be iterative customer and stakeholder engagement throughout the process. The trigger points are still a work in progress. (Written response June 2023: Our LTDS has been informed at every stage by customer insight. Our PR19 synthesis report provided a rich foundation to draw upon at the outset, many of the themes discussed in PR19 are relevant to the long-term and to LTDS. We have also drawn on newer research undertaken to inform the AMP8 plan, WRMP and DWMP. Where there were gaps in our understanding / specific requirements in the Ofwat LTDS guidance, we have undertaken new research. These projects are driven primarily by the LTDS however they have been undertaken to provide as much relevant insight as possible and they will inform other parallel workstreams. Research outputs will be incorporated into the Synthesis report.) | ICG Meeting 10 May 2022 and written response in June 2023 | Closed
17 | Long-term delivery strategy | 10 May 2022 ICG meeting | Challenge/information | What does the different scenario testing look like between the two extreme temperatures (e.g. 2 vs 4°C), which would create very different parallel business plans. | Response: Ofwat requires AW to put forward a lower environmental ambition future pathway and an adaptive plan. But there are real challenges. Being fit for 4°C future requires a different set of strategies from a 2°C future. (Written response in June 2023: The scenario testing work we are doing as part of LTDS demonstrates that several elements of our strategies are impacted by the more adverse scenarios. We are still working through the alternative pathways and will be writing up this work over the summer.) | ICG Meeting 10 May 2022 and written response in June 2023 | Closed
11 | Long-term delivery strategy | 12 April 2022 CEF meeting | Challenge | There might be a danger of pushing investments to the end of the LTDS and this needs to be scrutinised. | Response: the WRMP process helps to guard against this; it isn't AW's thinking to push decisions to the end of the 25-year period but it is certainly something to be scrutinised by the ICG. (Written response June 2023: As part of the development of LTDS, we need to consider when investment needs to be made. We need to consider affordability, customer priorities and intergenerational fairness. We also need to consider what the most efficient delivery schedule is, ensuring that we are preparing for a wide range of plausible futures (doing everything we need to do in the short term to keep options open and prepare for different eventualities) with making investment than is later not needed or superseded by new technologies.) | CEF Meeting 12 April 2022 and written response in June 2023 | Closed
12 | Long-term delivery strategy | 12 April 2022 CEF meeting | Challenge | Was a new Strategic Direction Statement needed. Why was there no mention of bathing water or affordability in the LTDS? | Response: long-term SDS ambitions will still hold as AW develops the LTDS and Business Plan. This sets a direction of travel and the LTDS will pick up on the more detailed issues. (Written response in June 2023: hese items will be captured as part of the LTDS preparation. Strategic Direction remains relevant and captures our headline challenges effectively. The LTDS will set out the next layer of detail.) | CEF Meeting 12 April 2022 | Closed
WINEP
155 | WINEP/WRMP | 15 September 2023 ICG meeting | Challenge/information | It would be useful to know what AW has changed in response to EA letters asking companies to model deferred investment pathways | Addressed during 15 September ICG meeting | 15 September 2023 ICG meeting | Closed
135 | WINEP | 16 June 2023 ICG meeting | Challenge/information | Was there any way to make WINEP more transparent for customers? | It was disappointing that WINEP was more output based but A-WINEP was a chink of exciting outcomes, which had received good support from a recent meeting with EA. AW was proposing a partnership centre of excellence to make sure each pound invested goes further for customers. They were looking for innovative ideas and had a pot of funding to invest in certain catchments including Southend and Great Yarmouth (spongy cities). | 15 September 2023 ICG meeting | Closed
64 | WINEP/bespoke performance commitments | 6 Oct 2022 ICG meeting | Challenge/information | Members wanted to see WINEP and advanced WINEP plans | On agenda for December 2022 meeting | 15 September 2023 ICG meeting | Closed
20 | WINEP/bespoke performance commitments | 10 May 2022 ICG meeting | Challenge/information | Members would like a chance to hear about WINEP and bespoke performance commitments | Response: bespoke performance commitments would come to the meeting in January 2023. WINEP to be discussed in December meeting. |  | Closed
WRMP
138 | WRMP | 16 June 2023 ICG meeting | Challenge/information | ICG members wanted to know what had changed since the draft, including NHH customer demand and incentives for customer behaviour. | This was addressed at the 30 June ICG meeting | 30 June 2023 ICG meeting | Closed
142 | WRMP | 30 June 2023 ICG meeting | Challenge/information | - Has the company tested customer support for investments to promote demand management vs new infrastructure (such as reservoirs)? | This was addressed at the 30 June ICG meeting | 30 June 2023 ICG meeting | Closed
143 | WRMP | 30 June 2023 ICG meeting | Challenge/information | - How effective is the installation of Smart Meters for demand management, as compared to interventions such as hosepipe bans? Has the company tested customer support for these measures, side by side? | This was addressed at the 30 June ICG meeting | 30 June 2023 ICG meeting | Closed
144 | WRMP | 30 June 2023 ICG meeting | Challenge/information | - Could we see more evidence around reducing Non-Household (NHH) customer demand and the environmental impact of the current plan? Follow up question: could there be more ambition based on savings through smart meters? | This was addressed at the 30 June ICG meeting. In response to follow up question: more information to be provided and circulated. This was seen as the beginning of the NHH journey. | 30 June 2023 ICG meeting | Closed
145 | WRMP | 30 June 2023 ICG meeting | Challenge/information | What has changed since the draft WRMP in response to customer engagement and why? | This was addressed at the 30 June ICG meeting | 30 June 2023 ICG meeting | Closed
146 | WRMP | 30 June 2023 ICG meeting | Challenge | To what extent can the reduction in demand provide the resilience that’s needed until such time as reservoirs and new supply side options come on stream? | AW has developed adaptive pathways, which include trigger points to divert to different plans based on changing circumstances in demand management, which are closely monitored. AW is working with EA and NE on this | 30 June 2023 ICG meeting | Closed
147 | WRMP | 30 June 2023 ICG meeting | Challenge | Were customers engaged on the level of challenges over the next planning period (e.g. about environmental improvements and resilience to more frequent hot, dry summers) | AW's engagement efforts compared to previous engagement had gained better insights on these big issues. AW had a robust understanding based on customer feedback and emphasised that AW has the lowest PCC of any water company in England. | 30 June 2023 ICG meeting | Closed
148 | WRMP | 30 June 2023 ICG meeting | Challenge | What was the potential for disruptive innovation - it was important to be open to digital innovations |  |  | Open
149 | WRMP | 30 June 2023 ICG meeting | Challenge | How was AW preparing for peak demand incidents (as recently happened with South East Water)? | AW has conducted in-depth evaluations in each area to ensure the company is in a better position than other water companies to respond to peak demand. They are experienced in managing assets during hot, dry summers. AW conducts a summer wash-up after every summer to learn from any restrictions experienced and identify necessary investments. They use the lessons learned and aren’t complacent. |  | Closed
150 | WRMP | 30 June 2023 ICG meeting | Challenge | The significant increase in costs for leak reduction and the tangible environmental impact of this investment was questioned. Customers may confuse leakage reduction with lower bills, if this wasn’t explained really clearly. | AW was currently waiting for options to be decided on. Customers generally don’t understand the costs associated with fixing water mains. Ofwat targets are calling for a 50% reduction in leakage (with a potential cost of more than £20bn); AW don’t believe this is feasible and consider a 38% reduction more reasonable (costing £4.3bn by 2050). Most customers believe leakage should be reduced at any cost. AW has tried hard to balance the demand against the supply side options so that there are a range of options that provide resilience (while also considering bill impact). |  | Open
108 | WRMP/Non household customers | 20 Jan 2023 ICG meeting | Challenge | Why did the company's draft WRMP did not include a substantive programme to reduce non-household water demand when Ofwat have introduced a performance commitment to do this and the Environment Act target also includes a 9% reduction in NHH demand by 2038. | ICG member met with AW colleagues after the meeting. They explained that it is indeed a gap in the current plan but that the company is actively working to address it before the final WRMP looking at a range of options. They offered to share the headlines work with the ICG at a future meeting (maybe a 10-15 mins update this summer) and the member would remain in touch with them with respect to the detail. | 30 June 2023 ICG meeting | Closed
104 | WRMP | 20 Jan 2023 ICG meeting | Challenge | Why was AW’s draft WRMP was published 5-6 weeks later than expected. Was that an assurance issue? | There was a very minor issue to reconcile with Cambridge Water. It was nothing material. After submitting additional information, this cleared up any questions. It was nothing to do with assurance | 20 Jan 2023 ICG meeting | Closed
86 | WRMP | 9 Dec 2022 ICG meeting | Challenge/information | How can we be confident you’re maxing out and doing everything possible under heading of demand management (e.g. around public messaging around water reuse)? How is AW comparing to other companies, both in UK and overseas. | Response from AW at ICG meeting: it’s a conversation AW has been having with the Environment Agency. The company doesn’t put anything into the plan that they don’t believe they can achieve. They’re generally quite conservative in numbers put forward because they like to be able to be evidence-based. | 30 June 2023 ICG meeting | Closed
45 | Water Resources Management Plan | 20 July 2022 email | Challenge | Section 5.2 – Signs of Success. We were wondering about the reference to ‘informed’ customers at this point. It seems that there needs to be a distinction between ‘self-informed’ and ‘informed through a qualitative survey process’. The customers referred to in this section seem to fall in the category of the former. This is fine, as long as their views are balanced appropriately with customers who are informed in a more controlled manner through a structured survey. The views of the latter should probably take precedence. It would be useful just to have sight of how much of the research could be considered as ‘self-informed’ rather than ‘informed through a qualitative survey process’. |  | 30 June 2023 ICG meeting | Closed
40 | Water Resources Management Plan | 18 July 2022 ICG meeting | Challenge/information | Members wanted to understand about core growth scenarios and the effect of alternative growth assumptions on the WRMP and DWMP decisions and trigger points. | Response: AW has looked at a number of different scenarios. From regional modelling, they know that the reservoir selection is robust to a range of DI scenarios (growth + demand management). Lower DI benefit would benefit the environment, as discussed; higher DI would trigger more demand management and alternative supply schemes. | ICG meeting 18 July 2022 | Closed
38 | Water Resource Management Plan | 18 July 2022 ICG meeting | Challenge/information | Members wanted to see more detail about how customers have shaped AW’s Best Value Plan? How has customer insight been used? | Response: AW first engaged qualitatively at a regional level. The synthesis report was used to drive the Best Value Plan. More details were offered to ICG members, as required. | ICG Meeting 18 July 2022 | Closed
18 | Water Resources Management Plan | 10 May 2022 ICG meeting | Challenge/information | ICG members highlighted the challenge of engaging customers on these topics and presenting the trade offs. Would there be an opportunity for the ICG to look at any customer engagement so far and challenge what evidence had been gathered and how it’s being used to develop the Best Value Plan? | Response: AW is currently developing a synthesis report to collate information for the IGC to scrutinise. CCW had seen some of the customer engagement but AW would be happy to pull the information together for members to scrutinise for July meeting. | ICG meeting May 2022 | Closed
14 | Water Resources Management Plan | 12 April 2022 CEF meeting | Challenge/information | What role would this Panel have in scrutinising customer engagement for the WRMP? | Response: There would be a deeper dive on the WRMP in the May meeting to understand more on how customers are being engaged and the materials being used. | CEF Meeting May 2022 | Closed
15 | Water Resources Management Plan | 12 April 2022 CEF meeting | Challenge/information | How were the views of Water Resources East stakeholders being fed into the process? | Response: some of WRE’s materials should be circulated to panel members, as they provide a good overview of longer term questions facing the region |  | Closed